## Sheet1
Module | Week | Task Name | Person Responsible | Estimated LOE | Due Date | Commit
Dev | Week 1 | JUnit test cases | Jaswin | 2 hours | Mar 30th,2022 | Mar 30th,2022
UI |  | Enhacements on UI | Vikram | 8 hours | March 31st,2022 | April 1st,2022
QA |  | Integrated Test cases | Lekha | 3 days
Day 1
Day 2
Day 3
Automation |  | NA