## Test Cases Sprint1
Your Company LOGO | Project Name: | Minions | Test Designed by: | Srilekha S
| Module Name: | Sign Up and Sign In | Test Designed date: | Feb 15th,2022
| Release Version: | V1 | Test Executed by: | Srilekha S
|  |  | Test Execution date: | Feb 18th,2022
Pre-condition | NA
Dependencies: | NA
Test Priority
UI
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
MNTC01 | App URL validation | Validation of application URL | Take a valid URL and check if we are landing on homepage | URL:http://localhost:8080/ | We need to land on our homepage URL | Landed Successfully | Passed
MNTC02 | Invalid App URL | Validation of invalid app URL | Try using an invalid URL and verify we are still able to navigate to our application homepage |  | The invalid URL should not enroute us to our application homepage | Didnt enroute successfully | Passed
MNTC03 | Sign In Page | Verify logging in with Valid Username and Password | Enter Valid Username and Password and click on login/Ok button | Username:bob12345 Password: P@ssword1 | User should able to successfully login | Successfullly logged In | Passed
MNTC04 | Sign In Page | Verify logging in with valid Username but invalid password | Enter valid username and invalid password then click on Ok button |  | User should not be able to login successfully. | Successfullly not logged In | Passed
MNTC05 | Sign In Page | Verify logging in with invalid Username but valid password | Enter invalid username and valid password then click on Ok button |  | User should not be able to login successfully. | Successfullly not logged In | Passed
MNTC06 | Sign In Page | Verify logging in with invalid Username and invalid password | Enter invalid username and invalid password then click on Ok button |  | User should not be able to login successfully. | Successfullly not logged In | Passed
MNTC07 | Sign Up page | Verify new User to be provided with 'Sign Up" link to sign up to the program | Validate if new User is able to click on "Sign Up" link and navigate to registration page. |  | User should able to successfully navigate to registration page. | Successfully navigated to Registration page | Passed
MNTC08 | Sign Up page | Verify all the mandatory fields on Registration page | Validate all the below fields are filled up on Registration page - 1.Username 2.Password 3.Confirm Password. 4.Already User ? text beneath Confirm password with "Sign In" link |  | User should able to successfully fill all the mandatory fields and click on "Ok" button | Successfully filled all the details | Passed
MNTC09 | Sign Up page | Verify negative check on mandatory fields on Registration page | Validate by not filling up any of above fields and page should prompt you to fill it to finish your registration |  | User should be prompted with "Fields should not be empty" when on clicking ok button without filling up details | Successful display of "Fields should not be empty" | Passed
MNTC10 | Sign Up page | Verify the Username strength created | Validate the Username entered meets up the criteria of - 1.Should be minimum of 8 chars in length. 2.Atleast one numeric or special character. 3.Username shall not include any spaces. 4.Username must contain at least one upper case letter. |  | User should be able to successfully create a Username which meets up the criteria. | Successfully created User with specific criteria. | Passed
MNTC11 | Sign Up page | Verify the Password strength created | Validate the password entered meets up the criteria of strong password- 1.Should be minimum of 8 chars in length. 2.Atleast one numeric or special character. 3.Password shall not include any spaces. 4.Password must contain at least one upper case letter. |  | User should be able to successfully create a password which meets up the strong password criteria. | Successfully created password with specific criteria. | Passed
API
MNTC12 | API | Valid the Host URL | Validate the Local server http://localhost:8080 | http://localhost:8080/ | User should successfully connect to Local server | User successfully connects to server | Passed
MNTC13 | API | Valid Username and Password | Validate when provided valid Username and password,we get a valid response | http://localhost:8080/users/signin?username=bob&password=password http://localhost:8080/users/signup?username=bob&password=password http://localhost:8080/users/signout?username=bob&password=password | Valid response or status code should be : 200-Ok | Response code is successful as 200 OK | passed
MNTC14 | API | Valid Username and Invalid Password | Validate when provided valid Username and Invalid password,we get a corresponding response | http://localhost:8080/users/signout?username=bob&password=passw | For Incorrect User details 401 – Access denial due to incorrect credentials | Response code is successful for invalid credentials as 401 OK | passed
MNTC15 | API | Invalid Username and valid Password | Validate when provided Invalid Username and valid password,we get a corresponding response | http://localhost:8080/users/signout?username=bob&password=passw | For Incorrect User details 401 – Access denial due to incorrect credentials | Response code is successful for invalid credentials as 401 OK | passed
MNTC16 | API | Invalid URL validation | When provided invalid URL, Corresponding Status code to be displayed as response | http://localhost:8080/users/signout?username=&password= | 400 – The request was not properly formed | Resposne code is successful for Invalid URL as 400 | passed
MNTC17 | API | Server connection validation | Validate when server connection fails,corresponding Status code is displayed |  | 500 – The server threw an error | Response code is successful forServer connection error as 500 | passed
DB
MNTC18 | Database | Validate the Database connection | Validate the credentials are stored successfully on registering for web portal |  | Credentials should satisfy the below criteria: Table: user  Column: userid integer – primary key unique sequence number  Column: username string – user name from sign up  Column: password string – password from sign up | Details are successfully stored in DB | Passed

## Report Day 1
Test Case# | Test Title | Status | Ran By | Comments
MNTC01 | App URL validation | Not Started | Jaswin
MNTC02 | Invalid App URL | Not Started | Jaswin
MNTC03 | Sign In Page | Not Started | Jaswin
MNTC04 | Sign In Page | Not Started | Jaswin
MNTC05 | Sign In Page | Not Started | Vikram
MNTC06 | Sign In Page | Not Started | Vikram
MNTC07 | Sign Up page | Pass | Vikram
MNTC08 | Sign Up page | Pass | Vikram
MNTC09 | Sign Up page | Pass | Vikram
MNTC10 | Sign Up page | Pass | Vikram
MNTC11 | Sign Up page | Pass | Lekha
MNTC12 | API | Pass | Lekha
MNTC13 | API | Pass | Lekha
MNTC14 | API | Pass | Lekha
MNTC15 | API | Pass | Lekha
MNTC16 | API | Pass | Lekha
MNTC17 | API | Pass | Lekha
MNTC18 | Database | Pass | Jaswin
Total Test cases | Title | Failed | Passed | Not Started
2 | App URL validation | 0 | 2 | 0
4 | Sign In Page | 0 | 0 | 4
5 | Sign Up page | 0 | 5 | 0
6 | API | 1 | 5 | 0
1 | Database | 0 | 1 | 0

## Report Day 2
Test Case# | Test Title | Status | Ran By | Comments
MNTC01 | App URL validation | Pass | Lekha
MNTC02 | Invalid App URL | Pass | Lekha
MNTC03 | Sign In Page | Pass | Lekha
MNTC04 | Sign In Page | Pass | Lekha
MNTC05 | Sign In Page | Pass | Vikram
MNTC06 | Sign In Page | Pass | Vikram
MNTC07 | Sign Up page | Pass | Vikram
MNTC08 | Sign Up page | Pass | Vikram
MNTC09 | Sign Up page | Pass | Vikram
MNTC10 | Sign Up page | Pass | Vikram
MNTC11 | Sign Up page | Pass | Lekha
MNTC12 | API | Pass | Jaswin
MNTC13 | API | Pass | Jaswin
MNTC14 | API | Pass | Jaswin
MNTC15 | API | Pass | Jaswin
MNTC16 | API | Pass | Jaswin
MNTC17 | API | Pass | Jaswin
MNTC18 | Database | Pass | Jaswin
Total Test cases | Title | Failed | Passed | Not Started
2 | App URL validation | 0 | 2 | 0
4 | Sign In Page | 0 | 4 | 0
5 | Sign Up page | 0 | 6 | 0
6 | API | 0 | 5 | 0
1 | Database | 0 | 1 | 0

## Test Cases Sprint2
Your Company LOGO | Project Name: | Minions | Test Designed by: | Srilekha S
| Module Name: | Landing and Settings page | Test Designed date: | Mar 15th,2022
| Release Version: | V1 | Test Executed by: | Srilekha S
|  |  | Test Execution date: | Mar 18th,2022
Pre-condition | Must Successfully Login
Dependencies: | Testcases from Sprint 1
Test Priority
UI
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
MCTC19 | App URL validation | Validation of application URL | Take a valid URL and check if we are landing on homepage | https://newsapi.org | We need to navigate to our landing page URL | Successfully navigated to URL | Pass
MCTC20 | Application default content validation | Default content validation | Validate the content available on URL when not logged in |  | App Url should be able to show: list of news articles on the landing page with "sign in" link display on right top of the page | Successful display of list of articles on landing page with respective links | Pass
MCTC21 | Application default content validation | Default content validation | Validate the content available on URL when logged in |  | App Url should be able to show: list of news articles on the landing page with "Username" displayed on right top of the page | Successful display of Username and corresponding elements on Landing page. | Pass
MCTC22 | Application default content validation | Default content validation | Validate the elements present on landing page when logged In and not logged In |  | When not logged in below elements are to be displayed on landing page: 1. My App 2.Refresh button 3.Sign in link When Logged in : 1. My App 2.Regresh button 3.Settings button. 4. Username text on right top. 5.Sign out link above the Username text | Successfull display of : 1. My App 2.Refresh button 3.Sign in link when not logged In and When Logged in : 1. My App 2.Regresh button 3.Settings button. 4. Username text on right top. 5.Sign out link above the Username text | Pass
MCTC23 | Setting page Validation | Settings page content validation | Click on "Settings" link on landing page |  | When clicked on "Settings"button, it should successfully navigate to Settinngs page | Successful navigation to settings page. | Pass
MCTC24 | Setting page Validation | Settings page content validation | Validate content on Settings page |  | Validate if the User is able to view the below preferences on settings page: With Text :" Choose your areas of interest" 1. General. 2. Business. 3. Entertainment. 4. Health. 5. Science. 6. Sports. 7. Technology and Ok and Cancel buttons. | Successful display of all the categories: " Choose your areas of interest" 1. General. 2. Business. 3. Entertainment. 4. Health. 5. Science. 6. Sports. 7. Technology and Ok and Cancel buttons. | Pass
MCTC25 | Setting page Validation | Settings page functionality check | Validate selection of preferences |  | Validate if the User is able to select atleast one preferance from the mentioned list | By default selection of alteast one preferance is successfully displayed | Pass
MCTC26 | Setting page Validation | Settings page functionality check | Validate selection of preferences |  | Validate if the User is able to select multiple preferences on mentioned list. | Successful selection of multiple preferences | Pass
MCTC27 | Setting page Validation | Settings page functionality check | Validate Ok button |  | Upon selection of preferences, User should able to successfully click on "Ok" button and navigate to Landing page | Page navigates successfully to Landing page upon selection of preferences and clicking OK | Pass
MCTC28 | Setting page Validation | Settings page functionality check | Validate Cancel button |  | Upon selection of preferences, User should able to successfully click on "Cancel" button and to re-select the prefrences again on settings page | Upon clicking Cancel, User is successfully able to re select the preferances. | Pass
MCTC29 | Setting page Validation | Settings page functionality check | Validate checked "Areas of Interest" |  | After selection of "Areas of Interest", navigate back to Settigns page and see if the options are still checked | upon certain selection and navigating back to settings page, we could not see selected preferances | Fail
API
MCTC30 | API | Valid the Host URL | /new/{user}/{category} |  | Valid response or status code should be : 200-Ok | Response code is 200-OK | Pass
MCTC31 | API | Valid the Host URL when not signed In |  |  | Valid response or status code should be : 200-Ok | Response code is 200-OK | Pass
MCTC32 | API | Invalid URL validation |  |  | 400 – The request was not properly formed | Response code is 400 | Pass
MCTC33 | API | Invalid Username and valid Password | Validate when provided Invalid Username and valid password,we get a corresponding response |  | For Incorrect User details 401 – Access denial due to incorrect credentials | Response code is 401 | Pass
DB
MCTC34 | DATABASE | User ID in Database | Validate data type |  | Check if the User ID is allocated as Primary key with below contraints:Column: userid integer – primary key unique sequence number | User ID is allocated with Primary key with Integer data type | Pass
MCTC35 | DATABASE | Username/Passwrod in DB | Validate data type |  | Username and Password should be of String type. | User name and Password are allocated with String type successfully. | Pass
MCTC36 | DATABASE | Category selection | Validate Selected Category data type |  | For any selected category, Data type should be "Boolean" with its value as "1" and not selected as "0" | Data type for selected category is displayed as "1" successfully. | Pass
MCTC37 | DATABASE | Category selection Negative check | Category removal on UI |  | On successfull removal of prefrence on UI, accordingly changes should be reflected in DB | Changes made on UI are successfully reflected in DB | Pass
MCTC38 | DATABASE | Username deletion | Deletion check |  | On removal of Username from DB, User should not be able to login on UI | Successfully cant login when Username is removed | Pass
MCTC39 | DATABASE | Password change | Password edit on DB/UI |  | Any change made on Password either on UI or DB to be updated accordingly. | Succesful change on password in DB is reflected on UI. | Pass

## Sprint2-Report 1
Test Case# | Test Title | Status | Ran By | Comments
MCTC19 | App URL validation | Pass | Lekha
MCTC20 | Application default content validation | Pass | Lekha
MCTC21 | Application default content validation | Pass | Lekha
MCTC22 | Application default content validation | Pass | Lekha
MCTC23 | Setting page Validation | Pass | Lekha
MCTC24 | Setting page Validation | Pass | Lekha
MCTC25 | Setting page Validation | Pass | Lekha
MCTC26 | Setting page Validation | Pass | Lekha
MCTC27 | Setting page Validation | Pass | Lekha
MCTC28 | Setting page Validation | Pass | Lekha
MCTC29 | Setting page Validation | Fail | Lekha
MCTC30 | API | Pass | Jaswin
MCTC31 | API | Pass | Jaswin
MCTC32 | API | Pass | Jaswin
MCTC33 | API | Pass | Jaswin
MCTC34 | DATABASE | Pass | Jaswin
MCTC35 | DATABASE | Pass | Jaswin
MCTC36 | DATABASE | Pass | Lekha
MCTC37 | DATABASE | Pass | Lekha
MCTC38 | DATABASE | Pass | Lekha
MCTC39 | DATABASE | Pass | Lekha
Total Test cases | Title | Failed | Passed | Not Started
4 | App URL validation | 0 | 4 | 0
7 | Setting page Validation | 1 | 6 | 0
4 | API | 0 | 4 | 0
6 | Database | 0 | 6 | 0

## JUnit Report
TC# | <?xml version="1.0" encoding="UTF-8"?><testrun name="NewsControllerTest" project="project" tests="10" started="10" failures="0" errors="0" ignored="0">
<testsuite name="com.cs684.project.news.NewsControllerTest" time="1.496">
TC1 | <testcase name="testGetNewsInvalidUser" classname="com.cs684.project.news.NewsControllerTest" time="0.907"/> | Pass
TC2 | <testcase name="testSaveSettingsSuccess" classname="com.cs684.project.news.NewsControllerTest" time="0.394"/> | Pass
TC3 | <testcase name="testSaveSettingsEmptyCategory" classname="com.cs684.project.news.NewsControllerTest" time="0.012"/> | Pass
TC4 | <testcase name="testGetNewsBlankUser" classname="com.cs684.project.news.NewsControllerTest" time="0.029"/> | Pass
TC5 | <testcase name="testSaveSettingsInvalidUsername" classname="com.cs684.project.news.NewsControllerTest" time="0.011"/> | Pass
TC6 | <testcase name="testSaveSettingsEmptyUser" classname="com.cs684.project.news.NewsControllerTest" time="0.011"/> | Pass
TC7 | <testcase name="testGetNewsBlankCategory" classname="com.cs684.project.news.NewsControllerTest" time="0.018"/> | Pass
TC8 | <testcase name="testGetNewsEmptyUser" classname="com.cs684.project.news.NewsControllerTest" time="0.011"/> | Pass
TC9 | <testcase name="testGetNewsEmptyCategory" classname="com.cs684.project.news.NewsControllerTest" time="0.011"/> | Pass
TC10 | <testcase name="testGetNewsSuccess" classname="com.cs684.project.news.NewsControllerTest" time="0.092"/> | Pass
</testsuite>
</testrun>

## Test Cases Sprint 3
Your Company LOGO | Project Name: | Minions | Test Designed by: | Srilekha S
| Module Name: | Integration tests | Test Designed date: | Apr 2nd,2022
| Release Version: | V1 | Test Executed by: | Srilekha S
|  |  | Test Execution date: | Apr 4th,2022
Pre-condition | Must Successfully Login
Dependencies: | Testcases from Sprint 1 and Sprint 2
Test Priority |  |  | Integration-UI Navigation
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
MCTC40 | App URL validation | Validation of application URL | Take a valid URL and check if we are landing on homepage | https://newsapi.org | We need to navigate to our landing page URL | Successfully navigated to URL | Pass
MCTC41 | Modules Integrated on landing page | Default content validation | Validate the content integrated on URL when on landing page |  | App Url should be able to show: list of news articles "tabs" on the landing page with "sign in" link display on right top of the page | Successful display of list of articles on landing page with respective links | Pass
MCTC42 | Modules Integrated on Home page | Default content validation | Validate the content integrated on URL when on Home Page |  | App Url should be able to show: list of news articles "tabs" on the home page with "Username" displayed on right top of the page | Successful display of Username and corresponding elements on Home page. | Pass
MCTC43 | Verify user account details when login is success | Default content validation | Validate the elements present on Home page when logged In as particular User |  | When logged in, Username of respective User to be displayed on page | "Username' of the User who logged in should be displayed on right top of application | Pass
MCTC44 | Integration validation on Settings page | Settings page content validation | Validate Integration between DB and "Settings" page on Home page |  | When clicked on "Settings"button of respective User , it should display "categories" selected as checked on Settings page | The "Categories" which are enabled on DB should be accordingly integrated with Settings page of corresponidng User. | Pass
MCTC45 | Integration validation on Settings page | Settings page content validation | Validate Integration between DB and "Settings" page on Home page |  | Validate when any change made on Category selection ,it should be reflected accordingly in DB | Changes made by specific User in his account on categories should make necessary changes in DB for his account | Pass
MCTC46 | Modules Integrated on Home page | Home and Settings page Integration | Validate Integration between "Home" page and "Settings" page on Home page |  | Validate when selected specific category, the news articles are displayed accordingly on Home page tab | New articiles related to category selection are displayed under "Home" tab
API
MCTC47 | API | Valid the Success response on UI & DB connection | When on login with valid credentials stored in DB ,Connection should be successfully established |  | Valid response or status code should be : 200-Ok | Response code is 200-OK | Pass
MCTC48 | API | Validate success response on "Settings" page and DB connection | When selecting specific category and its reflection in DB, connection should be successfully established |  | Valid response or status code should be : 200-Ok | Response code is 200-OK | Pass
DB
MCTC49 | DATABASE | Add/Update Validation | Operation Check |  | For every database add/update operation logs should be added. | Results are added successfully to Database | Pass
MCTC50 | DATABASE | Data Validation | Validate data type |  | Check if the correct data is getting saved in the database upon a successful page submit. | Category selection is successfully stored in DB | Pass
MCTC51 | DATABASE | Null Values Validation | Value storage check |  | Check values for columns that are not accepting null values. | Empty values are not stored in DB | Pass
MCTC52 | DATABASE | Data Integrity | Data Integration between UI and DB |  | Check for data integrity. Data should be stored in single or multiple tables based on the design | Data displayed on UI is match and Integrated successfully with DB values via API calls | Pass
MCTC53 | DATABASE | Data Integrity | Data Integration between UI and DB |  | Check if data is committed to the database only when the operation is successfully completed | Category selected and when click on "Submit" are enabled accordingly in DB successfully | Pass
MCTC54
Functional Testcases
MCTC55 | Verify Home page | Modules on landing page | Display home page articles |  | All the articles should be displayed on header banner | User can successfully see all the articles displayed on ehader banner | Pass
MCTC56 | Verify Home page | Link to filter articles | Articles filtered as: Home (on by default) General Business Entertainment Health Science Sports Technology |  | All the articles should be displayed as filtered accordingly | User can successfully see all the articles as filtered as per given filter. | Pass
MCTC57 | Verify Home page | “Home” link will display articles | Display articles from the choosen categories |  | Displays articles from the categories chosen in the settings page | User can successfully see the articles from the categories that are chosen in the settings page | Pass
MCTC58 | News API check | Arrange article categories | Articles arranged in descending order |  | Descending order displayed with the most recent first | User can successfully see all the articles displayed as the most recent first | Pass
MCTC59 | News API check | Landing page display “Home” link | Landing page will display articles for the “Home” link |  | Landing page displays articles for the “Home” link upon signing | Upon signing user can see “Home” link articles | Pass
MCTC60 | News API check | “Home” highlighted | The currently selected link is highlighted. |  | First signed-in page is highligted | Upon signing the user can the the home page highlited | Pass
MCTC61 | News API check | Returns the articles | Articles returend from the user’s settings |  | Articles returend are in decending order starting with the most recent | Articles returend sucessfully and in decending order starting with the most recent | Pass
MCTC62 | Tabs | Check if the clicking one tab hides the content of another. | Current tab hides content of other tabs |  | When migrating through tabs it hides the content of other tabs | Sucessfully hide the content of other tabs in current tab | Pass
MCTC63 | Pagination | Check the paging 'previous' and 'Next' link status on first page. | When signing in can see the option to select pages. |  | Choose the page where yo wants to go | User can succesfully migrate from one page to another | Pass
MCTC64 | Pagination | Check the default count of records per page. | The number of pages will be displayed on each page |  | Valid page number displayed on each page | Each page Displays a specific number with it. | Pass
MCTC65 | Pagination | Last page does not Display next button | When reached to last page, no option to go further. |  | No pages after last page | User could not go beyond the last page. | Pass

## Sprint 3 Report
Test Case# | Test Title | Status | Ran By | Comments
MCTC40 | App URL validation | Pass | Lekha
MCTC41 | Modules Integrated on landing page | Pass | Lekha
MCTC42 | Modules Integrated on Home page | Pass | Lekha
MCTC43 | Verify user account details when login is success | Pass | Lekha
MCTC44 | Integration validation on Settings page | Pass | Lekha
MCTC45 | Integration validation on Settings page | Pass | Lekha
MCTC46 | Modules Integrated on Home page | Pass | Lekha
MCTC47 | API | Pass | Lekha
MCTC48 | API | Pass | Lekha
MCTC49 | DATABASE | Pass | Lekha
MCTC50 | DATABASE | Pass | Lekha
MCTC51 | DATABASE | Pass | Lekha
MCTC52 | DATABASE | Pass | Lekha
MCTC53 | DATABASE | Pass | Lekha
MCTC54 |  | Pass | Vikram
MCTC55 | Verify Home page | Pass | Vikram
MCTC56 | Verify Home page | Pass | Vikram
MCTC57 | Verify Home page | Pass | Vikram
MCTC58 | News API check | Pass | Vikram
MCTC59 | News API check | Pass | Vikram
MCTC60 | News API check | Pass | Vikram
MCTC61 | News API check | Pass | Vikram
MCTC62 | Tabs | Pass | Vikram
MCTC63 | Pagination | Pass | Vikram
MCTC64 | Pagination | Pass | Vikram
MCTC65 | Pagination | Pass | Vikram
Total Test cases | Title | Failed | Passed | Not Started
1 | App URL validation | 0 | 1 | 0
3 | Modules Integrated on landing page | 0 | 3 | 0
1 | Verify user account details when login is success | 0 | 1 | 0
2 | Integration validation on Settings page | 0 | 2 | 0
5 | DATABASE | 0 | 5 | 0
2 | API | 0 | 2 | 0
3 | Verify Home page | 0 | 3 | 0
3 | Pagination | 0 | 3 | 0